NATIONAL SOCIAL SECURITY FUND · UGANDA

NSSF SaveQuest

Prototype Deck Outline

#WeBelieveInU · Save For Your Dream

# NSSF SaveQuest — Prototype Deck Outline

Presentation for: NSSF EXCO / Board

Duration: 45–60 minutes (incl. Q&A)

Format: 24 slides + appendix backup

Brand: NSSF — #WeBelieveInU | Save For Your Dream

## Slide 1 — Title

- **Title:** NSSF SaveQuest — Gamified Member Engagement for Vision 2035

- **Subtitle:** Prototype Proposal & Pilot Programme

- **Presented by:** [Organisation Name]

- **Date:** June 2026

- **Visual:** NSSF logo + SaveQuest shield icon mockup

## Slide 2 — Agenda

1. Strategic context & Vision 2035 alignment

2. The problem we are solving

3. Introducing NSSF SaveQuest

4. Live prototype demo (10 min)

5. Platform architecture & integrations

6. User journeys (3 personas)

7. Pilot programme & budget

8. ROI & business case

9. Timeline & recommendation

10. Q&A

## Slide 3 — Strategic Context

- **Vision 2035:** 50% coverage | UGX 50T AUM | 95% satisfaction

- **Current state:** 3.35M members (11% of workforce), UGX 23.5T+ AUM

- **Gap:** 12M+ informal workers underserved; Smartlife Flexi needs engagement layer

- **MD quote:** *"Creating a willingness to save and building the capacity of Ugandans to save"* — Patrick Ayota

- **Visual:** 50:50:95 infographic

## Slide 4 — The Problem

- **Visual:** Problem statement icons (4 quadrants)

## Slide 5 — Why Telegram?

- **2M+ Ugandan Telegram users** — no app-store install

- **Informal sector access** — boda stages, markets, gig workers already on Telegram

- **Low data cost** — lightweight Mini App vs. full native app

- **Proven model** — URAPearls platform live for URA (adaptation, not greenfield)

- **Complements NSSF Go** — engagement layer, not replacement

## Slide 6 — Introducing NSSF SaveQuest

- **Tagline:** *Save For Your Dream — One Shield Point at a Time*

- **What it is:** Gamified Telegram Mini App for learning, saving habits, referrals

- **What it is NOT:** Payment processor, benefit adjudicator, or balance manager (those stay in NSSF Go)

- **Core modules:** Home | Learn | Services | Earn | Saver Network

- **Visual:** App shell mockup (5-tab navigation)

## Slide 7 — Shield Points Economy

- **Important:** Non-monetary — badges, certificates, leaderboard status only

- **Visual:** Three-tier shield graphic

## Slide 8 — Feature Overview

## Slide 9 — LIVE DEMO

- **Duration:** 10 minutes

- **Flow:**

1. Open Telegram → NSSF SaveQuest Bot

2. Onboarding quiz → earn White Shields

3. Save Daily streak

4. Financial Literacy module sample

5. Services → Smartlife Flexi deep link

6. Help widget → Sanyu handoff

- **Note:** Interactive prototype on staging environment

## Slide 10 — Architecture (Conceptual)

Members → Telegram / NSSF Go deep links
         ↓
    SaveQuest Engagement Layer
         ↓
    Admin Console (NSSF staff)
         ↓
    NSSF Core Systems (NSSF Go API, Sanyu, Smartlife)

- **Principles:** Complement not replace | Data minimisation | Sanyu first for account queries

- **Visual:** Architecture diagram (from Prototype Paper)

## Slide 11 — Integration with NSSF Ecosystem

## Slide 12 — User Journey: Boda-Boda Rider

1. QR at boda stage → Telegram bot

2. 3-min onboarding quiz → 100 White Shields

3. Prompt: "Start UGX 5,000/week with Smartlife Flexi"

4. Deep-link to NSSF Go → enroll

5. Daily Save Daily streak → Day 7 Blue Shield badge

6. Refer 2 colleagues → district leaderboard

- **Visual:** Journey map (6 steps)

## Slide 13 — User Journey: Formal Employee

1. HR sends SaveQuest link in payslip

2. Services → e-statement via NSSF Go

3. Financial Literacy module → certificate

4. Upload payslip → Blue Shield (admin approval)

5. Join Employer League → team quiz competition

## Slide 14 — User Journey: NSSF Admin

1. Admin console → review Contribution Verify queue

2. Approve → member gets Blue Shield + notification

3. Publish weekly Save Challenge

4. Analytics: Smartlife enrollments, quiz completion rates

## Slide 15 — URA → NSSF Feature Mapping

## Slide 16 — Pilot Programme

- **Duration:** 12 weeks post-build

- **Deliverable:** Pilot evaluation report with go/no-go recommendation

## Slide 17 — Pilot Success Metrics

## Slide 18 — Budget Options

- **Saving vs greenfield:** 43–60% (UGX 1.5–3.0B)

## Slide 19 — ROI Hypothesis (Conservative)

- **3-year ROI:** Platform cost ~UGX 2.7B vs. UGX 10B+ AUM mobilised → **>3.7× return**

## Slide 20 — Implementation Timeline

- **Total:** ~18 months to national launch

## Slide 21 — Risk Summary

## Slide 22 — Governance & Operations

## Slide 23 — Recommendation

1. Approve Option B — Pilot Programme (UGX 1.41B)

2. Appoint executive sponsor and ICT liaison

3. Proceed to Phase 0 — Discovery workshops (6 weeks)

4. Schedule EXCO prototype demo — Week 9

Immediate next step: Sign Phase 0 + Phase 1 contract (UGX 280M for prototype)

## Slide 24 — Thank You / Q&A

- **NSSF SaveQuest** — Save For Your Dream

- **#WeBelieveInU**

- Contact: [Name] | [Email] | [Phone]

- **Appendix available:** Full budget, business plan, prototype paper

## Appendix Slides (Backup)

### A1 — Detailed Phase Budget Breakdown

### A2 — Payment Schedule & Milestones

### A3 — Technology Stack & Security

### A4 — Admin Console Capabilities (26 modules)

### A5 — Content Curriculum Outline (40+ modules)

### A6 — Competitive Landscape (NSSF Go vs Sanyu vs SaveQuest)

### A7 — Boda-Boda Sector Opportunity (1.2M riders, UGX 550B potential)

### A8 — Source Platform Inventory (433 files, 139 APIs)

### A9 — Team & Resource Plan

### A10 — IP & Ownership Terms

## Presenter Notes

- **Slide 9 (Demo):** Have backup screen recording if live demo fails

- **Slide 18 (Budget):** Lead with Option B; mention Option A as lower-risk entry if EXCO hesitant

- **Slide 19 (ROI):** Emphasise these are conservative; actual impact likely higher with informal sector scale

- **Timing:** Keep demo to 10 min max; leave 15 min for Q&A

## Design Guidelines for Deck Production

- **Primary colour:** NSSF Navy (#0B3D2E or brand green from nssfug.org)

- **Accent:** Gold (#C9A227) for highlights and CTAs

- **Typography:** Clean sans-serif (Arial, Calibri, or NSSF brand font if available)

- **Imagery:** Uganda workforce diversity, mobile phones, savings metaphors (shield, nest egg)

- **Logo placement:** Top-right on all slides except title (centred)

CONFIDENTIAL — For NSSF Internal Review Only